## Most Updated
|  | Project Name | Local Sponsor | Consultant | Anticipated Bid Solicitation Date | Anticipated Construction Commencement | Fill R- Monuments | Sand Source | Anticipate Cubic Yardage | Expected Dredge/Equipment Type | Approximate Min and Max Water Depths of Dredge Operation | Approximate Distance from Source to Discharge | Known Environmental Windows or other Project Limitations | Notes
1 | SE | 2025 Jupiter Inlet Sand Trap Dredging | Jupiter Inlet District | Taylor Engineering | 2025-01-01 | 2025-03-01 | R-14 - R-16 (Palm Beach Co. R-mons) | Jupiter Inlet sand trap | 80,000 cy | hydraulic suction cutterhead | 21.5' | 3,500' | Beach placemtn operations and equipment demobilized from beach by April 30 | pay in the cut, clean medium sand
2 | SW | Captiva Island | CEPD | APTIM, Nicole Sharp | 2024-01-01 | May 1 - July 1, 2025 | R-84 to R-109 | Offshore | 1182000 | Hopper | Approx. 40' | 7 miles | Sea turtle monitoring and nest relocations required during nesting season; no restricted pipeline corridors | n/a
4 | NW | Pensacola Beach Renourishment | Santa Rosa Island Authority, Juan Lemos | Foth ¦ Olsen, Krista Egan | 2025-02-01 | 2025-11-01 | R-107.5 to R-150.5 | Offshore | 1,600,000 cy | Hopper | 60' to 80' | 4 miles | No work in the summer | n/a
5 | E | Dune Restoration south of Ponce Inlet | Volusia County, Niles Cyzycki | Intera, Mike Trudnak | 2025-02-01 | 2025-05-01 | R-160 to R-190 | Florida Inland Navigation District MSA 434-S DMMA | 500,000 CY | Cutter | NA | 3 to 8 Miles | N/A. | Hydraulic offloading of the MSA 434 - S DMMA onto the beach in New Smyrna Beach. The DMMA currently holds approximatley 500,000 cubic yards of beach compatible sand.
6 | NW | Western Destin Beach Restoration | Okaloosa County. Alex Fogg Natural Resources Chief | Taylor Engineering, Duncan Greer | 2025-03-01 | 2025-11-01 | R-17 - R-20.5 R-23.5 - R25.5 | Offshore Regionally Permitted Borrow Area | 150,600 cy | Cutter / Hopper | 40' - 50' | ~ 4 miles | Nov. through April only. Required pipeline cooridors. 500 meter turbidity mixing zone at beach. Screening required. | FEMA Category G Hurricane Sally
7 | SW | Pinellas County Beach Renourishment | Pinellas County | APTIM, Jacob Rice | April. 2025 | May. 2025 | R-56 to R-66; R-71 to R-108A; R-126 to R-128A; R-136 to R-142; R-144 to R-146 | John's Pass, Blind Pass, Pass-A-Grille, and Egmont Shoals Borrow Areas | 2,200,000 cy | Cutterhead; Clamshell | 10' to 30' | From ~0.25 to ~21 nautical miles | Required pipeline cooridors. Hardbottom with 300 foot buffer required. Sea turtle and smalltooth sawfish conditions. | Reourishment may be advertised as two projects, dependent on timeline and constructability.
8 | NE | Flagler County Dune and Beach Restoration Project - Reach II | Flagler County, Ansley Wren-Key | Foth ¦ Olsen LLC | 2025-05-01 | 2025-07-01 | R45 - R77 | offshore | 1,800,000 cy | hopper | 50'-65' | ~ 12 miles | MEC screening | seawalls at ~30% of properties; numerous public and private walkovers
9 | NW | St. Joseph Peninsula Beach Renourishment and Coastal Structures Project | Gulf County | MRD Associates, Inc. | May/Jun-25 | 2025-08-01 | R-100 to R-105.8 | Offshore | 800,000 cy | Hopper | 30' to 40' | ~9 miles | Currently restricted from construction during peak marine turtle nesting season | Multiple seawalls/upland retaining walls within landward limits of fill, includes construciton of eight submerged breakwaters
10 | CE | Vero Beach Sector 5 | Indian River County, Eric Charest | APTIM, Nicole Sharp | 2025-06-01 | 2025-11-01 | R70-R86 | Upland | 150,000 cy | N/A | N/A | N/A | November through April construction timeframe only. Not currently permitted for offshore sand source. | Some seawalls, some easements not currently executed - properties not participating. Project slated to address Hurricanes Ian and Nicole sand losses and background erosion experienced since out last nourishment event.
11 | NE | South Ponte Vedra FEMA Cat G Project | St Johns County | First Line Coastal | 2025-08-01 | 2025-12-01 | R-76 to R-102.5 | Offshore | 1,000,000 cy | Hopper | 40' to 53' | 9.5 Miles | Mechanical Screening for MEC, Tutle Season and Right Whale season, OFW turbidity restrictions | Seawalls and dune walkovers throughout the project footprint
12 | SW | Coquina Beach Restoration Project (FEMA Project) | Manatee County | Coastal Protection Engeneering | Aug/Sep-25 | 2025-11-01 | R-33 to R-41 | Longboat Pass | 74,800 cy (requested) 63,450 cy (revised by FEMA, R-33 to R-36 removed because it overlaps with taper of Federal project) | Cutterhead | -13' | ~3000 ft | N/A. Permits allow construction in sea turtle nesting and shorebird breeding seasons. | Further investigation needed to determine volume of sand available for dredging in the borrow source. Groins in fill location. FEMA status: currently under EHP review
13 | SE | South Lake Worth Inlet Sand Trap Expansion | Palm Beach County. Contact Andy Studt | Coastal Protection Engineering, Tom Pierro | Sept. 2025 | Jan. 2026 | Inshore Only | SLWI Sand Trap Expansion | ~115,000 cy | Hard Rock Excavator(s)/Punch | 5' to 18' | 3.5 to 10 miles | No blasting. Hard rock excavation anticipated, contractor with demonstrated experience required. Beneficial reuse/placement of dredge material in LWL. | Lateral expansion and deepening of existing interior SLWI Sand Trap.
14 | SW | South Siesta Key Beach | Sarasota County, Joseph Kraus | TBD | Late 2025 | Spring or Fall 2026 | R-67 to R-77 | Upland or Offshore | Storm damage repair plus maintenance sand up to ±500,000 CY | Truck Haul or Hopper Dredge | -38.0' NAVD to -47.0" NAVD | 6.2 to 8.7 miles if hopper dredge | Preferred window outside of sea turtle nesting season. Screening potentially required if offshore sand used. Possible Spring Break conflicts if truck haul.
15 | SW | Manasota Key Beach | Sarasota County, Joseph Kraus | TBD | Late 2025 | Spring or Fall 2027 | R-171 to R-183 | Upland | Storm damage repair plus maintenance sand up to ±250,000 CY | Truck Haul | N/A | N/A | Preferred window outside of sea turtle nesting season. Possible Spring Break conflicts if truck haul.
16 | SE | 2026 Jupiter Inlet Sand Trap Dredging | Jupiter Inlet District | Taylor Engineering | 2026-01-01 | 2026-03-01 | R-14 - R-16 (Palm Beach Co. R-mons) | Jupiter Inlet sand trap | 80,000 cy | hydraulic suction cutterhead | 21.5' | 3,500' | Beach placemtn operations and equipment demobilized from beach by April 30 | pay in the cut, clean medium sand
17 | SE | North County Comprehensive Shore Protection Project Segments 2 and 3. | Palm Beach County. Contact Andy Studt | Foth/Olsen, Steve Howard | Mar. 2026 | Nov. 2026 | R-19 to R-38 | Offshore borrow area | ~234,000 cy (Segment 2) ~ 610,000 cy (Segment 3) | Trailing Suction Hopper Dredge | 64' to 72' | 2.3 to 5.7 miles | Nov. through March with additional approval required for April work. 200m by 1000 m turbidity mixing zone. Vibratory screening required. | Screened shell content ≥1% of dredge volume; offsite hauling of screened shell required.
18 | NE | Ponte Vedra Beach FEMA Cat G Project | St Johns County | TBD | TBD | 2026 | R-1 to R-46.2 | Offshore/Upland | TBD | Hopper/Truck Haul | TBD | 4.5 Mile | Mechanical Screening for MEC, Tutle Season and Right Whale season, OFW turbidity restrictions | Seawalls, Geotubes, and dune walkovers throughout the project footprint